## Sheet1
task-id | task | priority | description | adding-date | solved | estimated-finish-time (min) | connected-info | notes
1 | fixing terminal | A | fixing terminal | 2019-12-18 | 2019-12-23 | 15 | check in terminal the error message | https://stackoverflow.com/questions/32448174/creating-new-file-with-touch-command-in-powershell-error-message
2 | install-mindmanager | A |  | 2019-12-18 | 2019-12-19 | 4 | version: MindManager 2020 | https://www.mindjet.com/mindmanager/
3 | setting up coding environment | A | installing every program needed | 2019-12-22 | 2019-12-24 | 25 | bootstrap, nodejs, github, racket, react, firebase, vuejs, vuetify
4 | lighting up react | A | setting up it's environment | 2019-12-24 | 2019-12-24 | 5-10 per session | watch practical tut videos about it | https://www.youtube.com/watch?v=p6c7QA9ofvI&list=PLN3n1USn4xlntqksY83W3997mmQPrUmqM
5 | boosting up powershell | A | installing useful stuffs | 2019-12-24 | 2019-12-24 | 15 | like package managers and so on | active: choco, scoop, yarn
6 | fixing powershell | A | clarifying why yarn/npm start isn't functioning | 2019-12-24 |  | 20 | version is up to date; problem is still on; trying to unset host | error msg: 'react-scripts' is not recognized as an internal or external command, operable program or batch file. error Command failed with exit code 1.
7 | understanding firebase | B | how is it connected to the other languages | 2019-12-24 |  | 20 | read infos and watch practical tut videos about it | https://firebase.google.com/docs/projects/learn-more
Note on H2: Dia: defining it's function manually did the trick